## Agile Team
Agile Team - Orion
Name | Role
Srikanth Polisetty | Development Team
Vasudha Karri | Development Team
Rajesh Budithi | Development Team
Mohammad Mastan Baig | Development Team
Biju Paulose | Product Owner
Akshay Agarwal | Scrum Master

## Product Backlog
Epics
Epic# | Summary |  | Description | Acceptance Criteria
1 | Standard Pronunciation |  | Capability to manage the standard pronunciation of Employee names based on user roles along with the ability to search and play the existing audio samples for other employees | Scalable API solution Search and play standard pronunciation
2 | Preferred Pronunciation |  | Capability to override the existing pronunciation with a Preferred recording along with the ability to manage requests from employees through an approval workflow based on user roles | Override standard pronunciation Play and record preferred pronunciation Approve/Reject requests - Administrator
3 | Artifacts and Deliverables |  | Documentation of artifacts and deliverables to support the application purpose and funtionality | Application Playbook Technology Stack
Product Backlog (Stories)
Story ID | Epic | Summary | Description | Acceptance Criteria | Status | Story Points | Sprint | Priority | Comments
1 | Standard Pronunciation | Login - UI Display | Develop a login page to allow Wells Fargo employees to log in to the name pronunciation platform | Given I am a Wells Fargo employee When I enter valid user credentials Then I should be able to login to the platform | Done | 3 | 1
2 | Standard Pronunciation | Dashboard - UI Display | Develop a Dashboard for the name pronunciation platform after user login | Given I am a Wells Fargo employee When I have logged in to the platform as an Employee Then I should be routed to the Dashboard | Done | 5 | 1
3 | Standard Pronunciation | Admin - UI Display | Develop a screen to allow administrators to view approval requests | Given I am an Administrator When I login to the application UI Then the 'Admin' tab must be displayed | Done | 3 | 1
4 | Standard Pronunciation | Dashboard - People Search | Allow users to search for other employees by entering their details | Given I have logged in to the interface When I search for a user Then I should be able to look up the user profile | Done | 2 | 1
5 | Standard Pronunciation | People Search - Play standard pronunciation | Allow playback of standard pronunciation for users | Given I am on the user profile page When I click on Play button in the Standard Pronunciation widget Then the interface should play the standard pronunciation | Done | 3 | 1
6 | Standard Pronunciation | My Profile - Play standard pronunciation | Allow playback of standard pronunciation for the logged in user | Given I am on the Dashboard and the Standard Pronunciation widget is enabled When I click on the Play button Then I should be able to play the standard pronunciation | Done | 2 | 1
7 | Standard Pronunciation | Phonetics - Display | Display phonetics in the Standard Pronunciation widget | Given I am on the Dashboard When the Standard Pronunciation widget is enabled Then phonetics should be displayed | Done | 3 | 1
8 | Preferred Pronunciation | People Search - Play preferred pronunciation | Allow playback of preferred pronunciation for users | Given I am on the user profile page and the Preferred Pronunciation widget is enabled When I click on Play button in the Preferred Pronunciation widget Then the interface should play the preferred pronunciation | Done | 2 | 2
9 | Preferred Pronunciation | My Profile - Record preferred pronunciation | Allow end user to record an audio sample in the preferred pronunciation widget | Given I am on the Dashboard When I click on the Record button Then I should be able to record an audio sample for the preferred pronunciation | Done | 3 | 2
10 | Preferred Pronunciation | My Profile - Upload preferred pronunciation | Allow end user to upload an audio sample in the preferred pronunciation widget | Given I am on the Dashboard When I click on the Upload button Then I should be able to upload an audio sample for the preferred pronunciation | Done | 3 | 2
11 | Preferred Pronunciation | My Profile - Play preferred pronunciation | Allow playback of preferred pronunciation for the logged in user | Given I am on the Dashboard and the Preferred Pronunciation widget is enabled When I click on the Play button Then I should be able to play the preferred pronunciation | Done | 2 | 2
12 | Preferred Pronunciation | My Profile - Delete preferred pronunciation | Allow deletion of preferred pronunciation for the logged in user | Given I am on the Dashboard and the Preferred Pronunciation widget is enabled When I click on the Delete button Then I should be able to delete the preferred pronunciation | Done | 2 | 2
13 | Standard Pronunciation | My Profile - Logout | Allow the end user to logout from the application | Given I have logged in to the application When I click on the Logout button Then I should be logged out of the application | Done | 1 | 2
14 | Preferred Pronunciation | Admin - People Search - Record Preferred Pronunciation | Allow the administrator to record an audio sample for users via People Search | Given I have navigated to the user profile as an Administrator When the Preferred Pronunciation is not available Then I should be able to record an audio sample in the Preferred Pronunciation widget | Done | 3 | 2
15 | Preferred Pronunciation | Admin - People Search - Upload Preferred Pronunciation | Allow the administrator to upload an audio sample for users via People Search | Given I have navigated to the user profile as an Administrator When the Preferred Pronunciation is not available Then I should be able to upload an audio sample in the Preferred Pronunciation widget | Done | 3 | 2
16 | Preferred Pronunciation | Admin - People Search - Play Preferred Pronunciation | Allow the administrator to play the audio sample in the Preferred Pronunciation widget | Given I have navigated to the user profile as an Administrator When the Preferred Pronunciation is available Then I should be able to play the audio sample in the Preferred Pronunciation widget | Done | 2 | 2
17 | Preferred Pronunciation | Admin - People Search - Delete Preferred Pronunciation | Allow the administrator to delete the audio sample in the Preferred Pronunciation widget | Given I have navigated to the user profile as an Administrator When the Preferred Pronunciation is available Then I should be able to delete the audio sample in the Preferred Pronunciation widget | Done | 2 | 2
18 | Preferred Pronunciation | Admin - UI | Allow admin users to view approval requests for employees | Given I have logged in as Administrator When I am on the Admin tab Then I should be able to view the approval requests | Done | 2 | 3
19 | Preferred Pronunciation | Admin - Manage Approvals - Employee ID | Allow admin users to navigate to the user profile to approve or reject requests for Preferred Pronunciation | Given I am on the Admin tab When I click on the Employee ID hyperlink Then I should be routed to the employee's profile | Done | 3 | 3
20 | Preferred Pronunciation | Admin - Manage Approvals - Approve | Allow admin users to approve requests for Preferred Pronunciation | Given I am on the user's profile When I click on the Approve button Then the audio sample must be approved for the end user | Done | 3 | 3
21 | Preferred Pronunciation | Admin - Manage Approvals - Reject | Allow admin users to rejects requests for Preferred Pronunciation | Given I am on the user's profile When I click on the Reject button Then the audio sample must be rejected for the end user | Done | 3 | 3
22 | Artifacts and Deliverables | Application Playbook | Stepwise documentation of the actions to be performed on the application | Given the application UI and API have been developed When I click on the 'Download Playbook' link Then I should be able to download the application playbook | Done | 5 | 3
23 | Artifacts and Deliverables | Technology Stack | Details of the technology stack for the application | Given I am the product owner of a different product When I have the APIs ready Then I should be able to integrate in internal portals | Done | 5 | 3
Note on A9: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on F9: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on G9: Story Points or Ideal Days
Note on H9: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on I9: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## Sprint 1
1
2 hour iterations | 4 |  |  |  | Effort | Remaining
Trend calculated based on last x hours | 2 |  |  | Totals | 21 | 21 | 15 | 10 | 5
Task rows | 7 |  | Done days | 4 |  | 21 | 15.75 | 10.5 | 5.25
Warning! These are necessary |  |  | Trend |  |  | 20 | 15 | 10 | 5 | 0
template rows |  |  | Trend Days | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Stories | Story ID | Story Points | Responsible | Status | Est. | 20 1: 1; 15 2: 2; 10 3: 3; 5 4: 4
Login - UI Display | 1 | 3 | Vasudha | Done | 3 | 20 1: 3; 15 2: 2; 10 3: 1
Dashboard - UI Display | 2 | 5 | Srikanth | Done | 5 | 20 1: 5; 15 2: 4; 10 3: 3; 5 4: 1
Admin - UI Display | 3 | 3 | Rajesh | Done | 3 | 20 1: 3; 15 2: 3; 10 3: 2; 5 4: 2
Dashboard - People Search | 4 | 2 | Mastan | Done | 2 | 20 1: 2; 15 2: 1; 10 3: 1
People Search - Play standard pronunciation | 5 | 3 | Vasudha | Done | 3 | 20 1: 3; 15 2: 2; 10 3: 2; 5 4: 1
My Profile - Play standard pronunciation | 6 | 2 | Mastan | Done | 2 | 20 1: 2; 15 2: 1
Phonetics - Display | 7 | 3 | Rajesh | Done | 3 | 20 1: 3; 15 2: 2; 10 3: 1; 5 4: 1
21
Note on A4: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint 2
2
2 hour iterations | 4 |  |  |  | Effort | Remaining
Trend calculated based on last x hours | 2 |  |  | Totals | 23 | 23 | 17 | 11 | 6
Task rows | 10 |  | Done days | 4 |  | 23 | 17.25 | 11.5 | 5.75
Warning! These are necessary |  |  | Trend |  |  | 21 | 16 | 11 | 6 | 1
template rows |  |  | Trend Days | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Stories | Story ID | Story Points | Responsible | Status | Est. | 21 1: 1; 16 2: 2; 11 3: 3; 6 4: 4
People Search - Play preferred pronunciation | 8 | 2 | Srikanth | Done | 2 | 21 1: 2; 16 2: 1
My Profile - Record preferred pronunciation | 9 | 3 | Vasudha | Done | 3 | 21 1: 3; 16 2: 2; 11 3: 1; 6 4: 1
My Profile - Upload preferred pronunciation | 10 | 3 | Vasudha | Done | 3 | 21 1: 3; 16 2: 2; 11 3: 1; 6 4: 1
My Profile - Play preferred pronunciation | 11 | 2 | Mastan | Done | 2 | 21 1: 2; 16 2: 1
My Profile - Delete preferred pronunciation | 12 | 2 | Rajesh | Done | 2 | 21 1: 2; 16 2: 1; 11 3: 1
My Profile - Logout | 13 | 1 | Srikanth | Done | 1 | bar: 21 1
Admin - People Search - Record Preferred Pronunciation | 14 | 3 | Mastan | Done | 3 | 21 1: 3; 16 2: 3; 11 3: 2; 6 4: 1
Admin - People Search - Upload Preferred Pronunciation | 15 | 3 | Srikanth | Done | 3 | 21 1: 3; 16 2: 3; 11 3: 2; 6 4: 1
Admin - People Search - Play Preferred Pronunciation | 16 | 2 | Rajesh | Done | 2 | 21 1: 2; 16 2: 2; 11 3: 2; 6 4: 2
Admin - People Search - Delete Preferred Pronunciation | 17 | 2 | Rajesh | Done | 2 | 21 1: 2; 16 2: 2; 11 3: 2
23
Note on A4: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint 3
3
2 hour iterations | 4 |  |  |  | Effort | Remaining
Trend calculated based on last x hours | 2 |  |  | Totals | 21 | 21 | 15 | 9 | 3
Task rows | 6 | Done days | Done days | 4 |  | 21 | 15.75 | 10.5 | 5.25
Warning! These are necessary |  | Trend | Trend |  |  | 21 | 15 | 9 | 3
template rows |  | Trend Days | Trend Days | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Stories | Story ID | Story Points | Responsible | Status | Est. | 21 1: 1; 15 2: 2; 9 3: 3; 3 4: 4
Admin - UI | 18 | 2 | Vasudha | Done | 2 | 21 1: 2; 15 2: 1
Admin - Manage Approvals - Employee ID | 19 | 3 | Rajesh | Done | 3 | 21 1: 3; 15 2: 2; 9 3: 1
Admin - Manage Approvals - Approve | 20 | 3 | Vasudha | Done | 3 | 21 1: 3; 15 2: 2; 9 3: 1
Admin - Manage Approvals - Reject | 21 | 3 | Rajesh | Done | 3 | 21 1: 3; 15 2: 2; 9 3: 2; 3 4: 1
Application Playbook | 22 | 5 | Srikanth | Done | 5 | 21 1: 5; 15 2: 4; 9 3: 2; 3 4: 1
Technology Stack | 23 | 5 | Mastan | Done | 5 | 21 1: 5; 15 2: 4; 9 3: 3; 3 4: 1
21
Note on A4: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.